## Instructions for Use
How to use the SHarED Project Plan
West of England AHSN
The SHarED Project Plan is designed to support overall management of the project. It is presented as a Gantt chart which shows each steps that are necessary to implement the HIU service and support evaluation. It lists key activities, showing who is responsible for them along with their start and end dates, as well as highlighting project milestones.
Before starting, write your trust name in cell 'C4' as the West of England AHSN will ask to review your project plan to assist in tracking the progress being made by your team.
Dates
Make sure the dates align to your project. Week 1 indicates the start of the project funding and has been inputted to be the week commencing 3rd August. If your project starts at a different date, please adjust the dates as appropriate. By entering the first two dates, you can click and drag the dates along to the end of the table, always finishing at week 52. Please also adjust the start date in box C3.
Week 20 indicates the end of the project funding, however this date is likely to be extended for each trust due to staff leave. You can change this end date to suit your project by erasing the current black line to the right column 'AR' and drawing a new line next on the right side of the cells in the appropriate column.
Week 52 indicates the overall end of the SHarED project, at which time the evaluation will start.
Activity Column
The activities and key milestones are in column 'B'. These activities can be amended, however it is important to make sure that all components of the project are implemented and therefore it is not recommended that you remove rows. You may wish to add extra activities. This can be easily done by right clicking on the row below where you wish for the new row to go and pressing 'Insert'.
All activities are grouped in to themes, for example Training and Project Meetings/Calls. You can collapse and expand the groups by pressing the '-' and '+' buttons in column 1.
Person Responsible
The 'Person Responsible' column, 'C', describes who is responsible for completing each activity. While this document provides guidance on who may be best suited for each activity as outlined in Roles section in the toolkit, you may decide amongst the project team that a different team member is more appropriate. This can therefore be amended.
Colouring of Timescales
The cells in red are dates set by the West of England AHSN and for the most part relate to meetings and events. While these are adjustable in the document, it is asked that you do not edit them. The dates may change depending on all trusts availability, the Project Manager will let you know if this happens and you will be able to amend appropriately.
The cells in green are dates that are adjustable to suit your project. You can colour a cell green by simply writing 'r' in the cell. Similarly, to remove the green, delete 'r' and the cell will return to white.
The boxes can be changed to blue when you have completed a certain task by writing 'b' in the cell. It is recommended that you keep on top of changing colours as doing so will highlight whether the project is on track. To making tracking easy it is recommended that if some service components are already in place in your trust, for example the electronic alerts, you change this to blue at the beginning of the project and remove all adjacent remaining green cells, as opposed to deleting the whole row.
A number of activities are to be completed as a one off and others completed regularly. Additionally, some activities need to be completed at different points during the project. For example, it is recommended that you review your documentation, training resources and referral mechanisms utilising PDSA (Plan, Do, Study, Act) methodology and paperwork. Your changes will be discussed on the monthly calls to share ideas with the other trust.

## Project Plan
SHarED Project Plan
West of England AHSN
| Project Start Date: | 2020-08-03 | Week | -19 | -18 | -17 | -16 | -15 | -14 | -13 | -12 | -11 | -10 | -9 | -8 | -7 | -6 | -5 | -4 | -3 |  | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
| Trust: | xxx | Date | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23 | 2019-12-30 | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | COVID PAUSE | time axis 2020-07-20 to 2021-07-25
| Activity | Person Responsible *HIU Team = Clinical lead, ED Matron and HIU Co-ordinator | [19 empty] | 2020-08-10: *Week 1 indicates the start of project; 2020-12-21: *The end of week 20 indicates the end of the HIU co-ordinator and clinical lead funding from West of England AHSN assuming the role is started the w/c 03.08.2020. Depending on leave this end date is adjustable. | *The end of week 52 indicates the end of project
1 | Workshop | bar: 2020-07-20 to 2021-04-26; 2021-05-10; 2021-05-24; 2021-06-07; 2021-06-21; 2021-07-05; 2021-07-19 to 2021-07-25
1.1 | Workshop 1 | HIU Team |  |  |  | b
1.2 | Virtual Event | HIU Team | bar: 2020-08-03
1.3 | Workshop 2 | HIU Team | bar: 2020-10-05
1.4 | Workshop 3 | HIU Team | bar: 2020-12-07
2 | Role Appointment | bar: 2020-07-20 to 2021-04-26; 2021-05-10; 2021-05-24; 2021-06-07; 2021-06-21; 2021-07-05; 2021-07-19 to 2021-07-25
2.1 | Appoint HIU-Co-ordinator | Clinical lead/matron |  |  |  | b | b | b | b | b | b | b | b
2.2 | Agree contract and job description | Clinical lead/matron |  |  |  | b | b | b | b | bb | b | b | bb
2.3 | Return Memorandum of Understanding to Project Manager | Clinical Lead | bar: 2020-07-20
2.4 | Return DPIA and PISA to Project Manager | Clinical Lead | bar: 2020-07-20
2.3 | Start date for Co-ordinator and clinical lead | HIU Team | bar: 2020-08-03
3 | Coaching and Quality Improvement Training | bar: 2020-07-20 to 2021-04-26; 2021-05-10; 2021-05-24; 2021-06-07; 2021-06-21; 2021-07-05; 2021-07-19 to 2021-07-25
3.1 | Coaching training (optional) | HIU Co-ordinator |  |  |  |  | b
3.2 | QI Summer Series (optional) | HIU Co-ordinator | bar: 2020-07-27 to 2020-08-24
4 | Project Meetings/Calls | bar: 2020-07-20 to 2021-04-26; 2021-05-10; 2021-05-24; 2021-06-07; 2021-06-21; 2021-07-05; 2021-07-19 to 2021-07-25
4.1 | Monthly call with ED Matrons | HIU Co-ordinator | bar: 2020-08-17; 2020-09-14; 2020-10-12; 2020-11-16; 2020-12-21
4.2 | Monthly project management call with WEAHSN | HIU Co-ordinator/clinical lead | bar: 2020-08-31; 2020-09-28; 2020-10-26; 2020-11-30; 2021-01-04; 2021-01-25
5 | Data Collection | bar: 2020-07-20 to 2021-04-26; 2021-05-10; 2021-05-24; 2021-06-07; 2021-06-21; 2021-07-05; 2021-07-19 to 2021-07-25
5.1 | Send high level data set to Megan | HIU co-ordinator/Business Intelligence Team | bar: 2020-08-03; 2020-09-07; 2021-01-04; 2021-07-25
5.2 | Share monthly data set with Megan (once started 10 plans) | HIU Co-ordinator | bar: 2020-09-28; 2020-10-26; 2020-11-30; 2021-01-04; 2021-02-01; 2021-03-01; 2021-03-29; 2021-04-26; 2021-05-31; 2021-06-28; 2021-07-25
6 | Local Background Information | bar: 2020-07-20 to 2021-04-26; 2021-05-10; 2021-05-24; 2021-06-07; 2021-06-21; 2021-07-05; 2021-07-19 to 2021-07-25
6.1 | Gather local data | Clinical lead | [11 empty] | b | b | bb
6.2 | Analyse local data & pop'n needs | HIU Team | [13 empty] | bb
6.3 | Identify local stakeholders for MDT | HIU Team | [13 empty] | g
6.4 | Contact local stakeholders for MDT | HIU Co-ordinator | [14 empty] | g | g | g | bar: 2020-08-03 to 2020-08-24
7 | Finalise Pathway | bar: 2020-07-20 to 2021-04-26; 2021-05-10; 2021-05-24; 2021-06-07; 2021-06-21; 2021-07-05; 2021-07-19 to 2021-07-25
7.1 | Agree referral mechanism(s) | HIU Team | bar: 2020-08-03 to 2020-08-31; 2020-10-05 to 2020-10-19; 2020-11-30 to 2020-12-14
7.2 | Agree triage mechanism | HIU Team | bar: 2020-08-03 to 2020-08-31; 2020-10-05 to 2020-10-19; 2020-11-30 to 2020-12-14
7.3 | Set up alerts on system on clinical record system | HIU Co-ordinator | bar: 2020-08-03 to 2020-08-31
8 | Finalise and Review Documentation | bar: 2020-07-20 to 2021-04-26; 2021-05-10; 2021-05-24; 2021-06-07; 2021-06-21; 2021-07-05; 2021-07-19 to 2021-07-25
8.1 | Referral paperwork | HIU Co-ordinator/Clinical Lead | bar: 2020-08-03 to 2020-08-17; 2020-10-05 to 2020-10-19; 2020-11-30 to 2020-12-21
8.2 | Personal Support Plan | HIU Co-ordinator/Clinical Lead | bar: 2020-08-03 to 2020-08-17; 2020-10-05 to 2020-10-19; 2020-11-30 to 2020-12-21
8.3 | Governance Process | HIU Co-ordinator/Clinical Lead | bar: 2020-08-03 to 2020-08-17; 2020-10-05 to 2020-10-19; 2020-11-30 to 2020-12-21
8.4 | Patient leaflet | HIU Co-ordinator/Clinical Lead | bar: 2020-08-03 to 2020-08-17; 2020-10-05 to 2020-10-19; 2020-11-30 to 2020-12-21
8.5 | GP letter | HIU Co-ordinator/Clinical Lead | bar: 2020-08-03 to 2020-08-17; 2020-10-05 to 2020-10-19; 2020-11-30 to 2020-12-21
9 | Communications | bar: 2020-07-20 to 2021-04-26; 2021-05-10; 2021-05-24; 2021-06-07; 2021-06-21; 2021-07-05; 2021-07-19 to 2021-07-25
9.1 | Liaise with trust comms | HIU Co-ordinator/Clinical Lead | bar: 2020-08-31; 2020-09-28; 2020-10-26; 2020-11-23; 2020-12-21; 2021-01-18; 2021-02-08; 2021-03-01; 2021-03-22
9.2 | Raise awareness of project in ED | HIU Team | bar: 2020-08-31; 2020-09-28; 2020-10-26; 2020-11-23; 2020-12-21; 2021-01-18; 2021-02-08; 2021-03-01; 2021-03-22
10 | Training | bar: 2020-07-20 to 2021-04-26; 2021-05-10; 2021-05-24; 2021-06-07; 2021-06-21; 2021-07-05; 2021-07-19 to 2021-07-25
10.1 | Agree training methods | HIU Team | bar: 2020-08-03 to 2020-08-17
10.2 | Adapt training resources | HIU Team | bar: 2020-08-03 to 2020-08-17; 2020-10-05 to 2020-10-19; 2020-11-30 to 2020-12-14
10.3 | Deliver bite size training | HIU Co-ordinator | bar: 2020-08-24; 2020-09-21; 2020-10-19; 2020-11-16; 2020-12-14; 2021-01-11; 2021-02-01; 2021-02-22; 2021-03-15
11 | Project Delivery | bar: 2020-07-20 to 2021-04-26; 2021-05-10; 2021-05-24; 2021-06-07; 2021-06-21; 2021-07-05; 2021-07-19 to 2021-07-25
11.1 | Triage 6 patients using EDITT and PDSA tool | HIU Co-ordinator | bar: 2020-08-03; 2020-08-31; 2020-09-28; 2020-11-02; 2020-11-30
11.2 | Commence work with first patients | HIU Co-ordinator | bar: 2020-08-10
12 | Celebrate Progress | bar: 2020-07-20 to 2021-04-26; 2021-05-10; 2021-05-24; 2021-06-07; 2021-06-21; 2021-07-05; 2021-07-19 to 2021-07-25
12.1 | Regular updates to staff of progress e.g. printing infographic | HIU co-ordinator | bar: 2020-08-24; 2020-09-21; 2020-10-19; 2020-11-16; 2020-12-14; 2021-01-11; 2021-02-01; 2021-02-22; 2021-03-15
13 | Surveys | bar: 2020-07-20 to 2021-04-26; 2021-05-10; 2021-05-24; 2021-06-07; 2021-06-21; 2021-07-05; 2021-07-19 to 2021-07-25
13.1 | Culture Survey | Clinical Lead | bar: 2020-08-10 to 2020-08-24; 2020-11-30 to 2020-12-14; 2021-07-12 to 2021-07-25
13.2 | ICECAP-A pre-PSP | HIU co-ordinator | bar: 2020-08-10 to 2020-12-14
13.3 | ICECAP-A post-PSP (contact patient or send out letter) | HIU co-ordinator | bar: 2021-02-15; 2021-03-15; 2021-04-12; 2021-05-10; 2021-06-14; 2021-07-12
14 | Business case for ongoing funding | bar: 2020-07-20 to 2021-04-26; 2021-05-10; 2021-05-24; 2021-06-07; 2021-06-21; 2021-07-05; 2021-07-19 to 2021-07-25
14.1 | Write Case study | HIU Co-ordinator/Clinical Lead | bar: 2020-11-09 to 2020-11-16; 2021-07-12 to 2021-07-25
14.2 | Gather local data and analyse | HIU Co-ordinator/Clinical Lead | bar: 2020-11-09 to 2020-11-16; 2021-07-12 to 2021-07-25
14.3 | Send off business case | HIU Co-ordinator/Clinical Lead | bar: 2020-11-23; 2021-07-12 to 2021-07-25
14.4 | Awaiting response for business case | HIU Co-ordinator/Clinical Lead | bar: 2020-11-23 to 2020-12-14; 2021-07-12 to 2021-07-25